# RICD Funding Roadmap

## A Chronological Plan: Deadlines, Requirements, and What Needs Building

Dated as of August 29, 2026. Every deadline below is a real, verified date as of that day, not a general description of how these programs typically work -- checked directly rather than assumed. Funding deadlines and program terms change; this document should be re-verified against each program's own current page before acting on any date more than a few months old. This is a living plan, not a permanent record the way the manuscript and tracker documents are.

# Phase 0: Immediate — No Prerequisites, Start Now

These require no legal entity, no incorporation, and no additional building beyond what already exists (the validated tracker, the manuscript, the GitHub repository).

Emergent Ventures (Mercatus Center, George Mason University). Real, currently active — its 58th cohort was announced this week. Rolling applications, no fixed deadline, no academic or credential requirements stated (explicitly: "EV doesn't care about your credentials, your formal education, or your polished business plan"), decisions typically made within weeks. Grants range from roughly $1,000 to $50,000, occasionally more. A recent cohort included a grantee doing pure mathematics and theoretical physics work, confirming this program funds exactly this kind of theoretical, pre-commercial project. Application requirement: a short online form; no pitch deck needed to start. Recommended action: apply now, this week.

Begin building a real, investor-facing one-pager and short pitch deck. This is a genuine, distinct thing to build -- separate from the GitHub repository's academic framing, which is not written for a funder or angel investor skimming for 90 seconds. Needed before any angel or VC conversation; not needed for the Emergent Ventures application itself.

Begin angel outreach. AngelList profile and warm-introduction requests can start immediately; syndicate checks there typically run $25,000-$500,000 and close in two to four weeks once a lead commits. Deep-tech funds explicitly built for non-traditional-credential founders, and women-focused angel networks (Golden Seeds among them), are real, applicable options worth approaching once the one-pager above exists.

# Phase 1: Near-Term Prerequisites — Needed Before Any SBIR Application (Target: September-Early October 2026)

SBIR/STTR eligibility requires an actual registered small business -- this is a real, necessary legal step, not paperwork that can be skipped or done later.

1. Incorporate as a small business (LLC or C-corp) meeting SBA's small business size standards.

2. Register in SAM.gov (System for Award Management) -- required for any federal grant or contract, including SBIR.

3. Register in the SBA's SBIR Company Registry.

4. Submit an NSF SBIR/STTR Project Pitch (a mandatory three-page pre-screen under active solicitation NSF 26-510). NSF reviews these in roughly three weeks and only issues an invitation to submit a full proposal if the pitch is accepted -- a real, sequential gate, not a formality. Given the review lag, a Project Pitch should be submitted no later than early-to-mid October 2026 to leave time for review and a full proposal before the November deadline below.

# Phase 2: Real, Hard Deadline — November 4, 2026

NSF SBIR/STTR Phase I full-proposal deadline (solicitation NSF 26-510), if a Project Pitch invitation was received. Award size: Phase I up to $305,000 (6-18 months); Phase II up to $1,250,000 (roughly 24 months, invitation-only for Phase I awardees); Fast-Track up to $1,555,000 combining both phases. Historical Phase I funding rate is 10-20%, genuinely competitive. Note: NSF's own prior deadline this cycle, July 27, 2026, has already passed as of this document's date -- November 4, 2026 is the next real, viable target, not a missed opportunity to chase.

# Phase 3: Ongoing and Fallback Dates

March 4, 2027 -- the following NSF SBIR/STTR Phase I full-proposal deadline, a real fallback if the November window is missed or a Project Pitch invitation arrives too late to prepare a full November proposal.

DHS SBIR -- runs on an annual cycle, historically pre-solicitation in November with the window opening in January and closing mid-to-late January. This project's own most relevant DHS window has already closed for this cycle; watch for the next pre-solicitation around November 2026 for a window expected around January 2027. DHS explicitly funds "critical infrastructure resilience" and "predictive analytics for cyber risk" -- a strong match for the drift/cascade-prediction tracker specifically.

Institutional venture capital -- realistically the last step in this sequence, not the first. VC firms currently active in observability and infrastructure resilience (Sequoia's dedicated seed fund explicitly lists this as a current focus) generally expect at least a working pitch deck and some external validation -- an Emergent Ventures grant, angel commitment, or an SBIR award all function as exactly that kind of validation. Approaching institutional VC before any of the above exists is realistically premature.

# Requirements Checklist (Recap)

Needed for Emergent Ventures: nothing beyond what already exists. Needed for angel outreach: a real one-pager and short deck (to be built). Needed for any SBIR application: a registered small business entity, SAM.gov registration, SBA SBIR Company Registry registration, and (for NSF specifically) a submitted and accepted Project Pitch before the full-proposal deadline. Needed for institutional VC: the deck above, plus at least one real form of external validation from an earlier step in this sequence.